## Summary of Changes Review Log
Risk Register
PURPOSE: This document represents a summary of risk register updates
Risk Register updates and reviews should be performed at least quarterly in preparation for the ISPMS Quarterly Management Reviews, and in accordance with the “Risk Review Criteria” section of the MSI Common Risk Management Framework.
Risk Register Updates |  |  |  | Risk Register Reviews - To Be Reviewed Quarterly
Date | Version | Changes made by | Changes made | Review Date | Quarter | Year | Reviewer | All open Risks Reviewed? | New Risks Added? | Additional changes or notes
2024-01-16 | 1 | Ashwini Basavaraju Krishna Prasad M V MOSES George | 1) Quarterly Risk Register review is performed 2) Updated Risks: - R-24 [Low], reviewed treatment plan, target date moved to Q3 2024 - R-28 [Low], updated the treatment status, target date moved to Q1 2024 - R-29 [Low], treatment and risk status reviewed - R-30 [Major], treatment, risk level and details updated. | 2024-01-08 | Q4 | 2023 | Manjunatha Rajappa Krishna Prasad M V Ashwini Basavaraju | Yes | No
2024-02-09 | 2 | Manjunatha Rajappa Lakshmikanth Mannepalli Sharath Kumar T S Amit Kumar Krishna Prasad M V Suresh Thiriveedi Soma Basu Madhurya Soma | Added R-31 R-32 | 2024-02-09 | Q1 | 2024 | MOSES George Lakshmikanth Mannepalli Manjunatha Rajappa Krishna Prasad M V | No | Yes
2024-02-14 | 3 | Ashwini Basavaraju MOSES George | Added R-33 | 2024-02-09 | Q1 | 2024 | MOSES George Ashwini Basavaraju Krishna Prasad M V | No | Yes
2024-02-19 | 4 | MOSES George Christopher Poniecki | Closed R028 | 2024-02-19 | Q1 | 2024 | Krishna Prasad M V Christopher Poniecki Sanjeev Harohalli Upananda Singha | No | No
2024-04-16 | 5 | MOSES George | Closed R029 Updated R024 comments R030, R33 risk rating to medium as the occurrence of the incident is unlikely. Updated the status / remarks, and added Premdass under the treatment/risk owner. R031 Updated the satus / remarks R032 Updated the status / remarks | 2024-04-16 | Q1 | 2024 | Manjunatha Rajappa Ashwini Basavaraju Lakshmikanth Mannepalli | Yes | No
2024-04-22 | 6 | MOSES George | Updated R031 Risk details to include Azure and On Prem Lab env, Remarks / Status mentioning further mitigation controls and Actions | 2024-04-22 | Q2 | 2024 | Lakshmikanth Mannepalli Syed Nazir K Amit Kumar Sunil Katke | No | No
2024-05-09 | 7 | MOSES George | R030, R033 updated the treatment progress and dates. | 2024-05-09 | Q2 | 2024 | Premdass Amaladass Venkat Venugopal Ashwini Basavaraju Krishna Prasad M V | No | No
2024-06-14 | 8 | Ashwini Basavaraju MOSES George | R024, R030, R033 updated the treatment progress and dates. Closed the risk. | 2024-06-13 | Q2 | 2024 | Ashwini Basavaraju MOSES George Manjunatha Rajappa | Yes | No
2024-07-24 | 9 | MOSES George | R031 - Progress updated and moved the mitigation date to end of Q3-2024 | 2024-07-24 | Q3 | 2024 | Syed Nazir K Sunil Katke Lakshmikanth Mannepalli | Yes | No
2024-10-01 | 10 | MOSES George | R031 - Progress updated and moved the mitigation date to end of Q4-2024 | 2024-10-01 | Q4 | 2024 | Lakshmikanth Mannepalli | Yes | No
2025-01-09 | 11 | MOSES George | R031 - Progress updated and moved the mitigation date to end of Jan-2025 | 2025-01-09 | Q4 | 2024 | Lakshmikanth Mannepalli | Yes | No
2025-03-24 | 12 | MOSES George | R031 - Pending confirmation from Syed and Lakshmikanth to close the Risk | 2025-03-24 | Q1 | 2025 | Lakshmikanth Mannepalli | Yes | No
2025-07-07 | 13 | MOSES George | R031 - Pending confirmation from Syed and Lakshmikanth to close the Risk, moved target date to Q3 end | 2025-07-07 | Q2 | 2025 | Lakshmikanth Mannepalli | Yes | No
2025-09-25 | 14 | MOSES George | R031 - Pending confirmation from Syed and Lakshmikanth to close the Risk | 2025-09-25 | Q3 | 2025 | MOSES George Krishna Prasad M V | Yes | No
2025-12-17 | 15 | MOSES George | Reviewed all closed and open risks in old register and current register with respective risk managers and owners Moved following risks from old register to current as part of review of closed risks which may need a monitoring cadence R010, R011, R012, R016 (Monitor) Updated following in new register to monitor R024, R031 Document owner changed to MOSES George | 2025-12-05 | Q4 | 2025 | MOSES George Krishna Prasad M V Lakshmikanth Mannepalli Ashwini Basavaraju Sharath Kumar T S | Yes | No
2026-01-16 | 16 | MOSES George | R016, R024, monitoring not needed. Noted MSI Global IT team updates on Jira data Backup policy R010, R011, R012, R031 (Monitor) | 2026-01-16 | Q1 | 2026 | Ashwini Basavaraju MOSES George Krishna Prasad M V | Yes | No
2026-04-02 | 17 | MOSES George | R031 (Qtrly Monitoring, review done) R010, R011, R012 (Monitor, review in Q2) R034 added for 4th floor unavailability of MSI access control systems R035 added for 4th floor shared server room access control process gaps where MSI secure rack/equipement is seated | 2026-04-02 | Q2 | 2026 | Lakshmikanth Mannepalli Krishna Prasad M V Prem Dass Amaladass Sridhara SV (CBRE) | Yes | Yes
Document owner: |  |  | MOSES George
Document classification: | Motorola Solutions Confidential Restricted
Link To Bangalore Information Asset Register: | Bangalore Information Asset Register v3.0 (Core)
Link To Legacy Bangalore Information Asset Register: | CCS Bangalore Risk Register UPDATED
Link To Common Risk Management Framework
Link To Common Risk Management Framework Appendix
NOTE
We review risks newly added/removed, status as part of ISMS reviews in Quarterly MR.

## Risk Register
| Step 1: Risk Identification | [5 empty] | Step 2: Risk Assessment Refer to the "Risk Guide" tab |  |  |  | Step 3: Risk Response/Treatment | [10 empty] | Step 4: Risk Monitoring / Closure
Risk I.D. | Corresponding Information Asset I.D. / Link | Asset | Date Risk Identified | Risk Owner | Risk Description; Threat/Vulnerability Summary w/ Potential Effect | Existing Mitigating Controls / Policies | Inherent Impact | Inherent Likelihood | Inherent Risk Ranking | Inherent Financial Impact | Treatment Decision | Treatment Plan / Controls To Be Implemented | Treatment Owner | Target Completion Date | Update / Progress ***This cell should contain ALL treatment status updates, as well as dates | Treatment status | Treatment Completion Date | Residual / Current Impact | Residual / Current Likelihood | Residual / Current Risk Ranking | Residual/Current Financial Impact | Monitoring Cadence | Next Review Date | Closure date | Risk Owner & Title | Closed risk for monitoring cadence, Review 11/26/2025 12/5/2025 | Remarks
0 | NA | Building Security / Access THIS IS MEANT TO BE AN EXAMPLE - PLEASE UPDATE AS NECESSARY | 2023-07-12 | Tom Jones | “As a result of insufficient building access controls, there is a risk that assets will be vulnerable to unauthorized access, which may result in theft, and loss of confidentiality of proprietary information” | MSI Loss Prevention and Security controls in place per applicable ISMS policies. Tour and Show Physical Security | 4 - Severe ($3M - $10M, 20% - 30%) | 2 - Unlikely (11% - 40%) | 17 | $15M |  | Hire a front desk host to monitor entry, add cameras to monitor activity, ensure badge access controls are working | Tom Jones | 2023-09-12 | ~ 12-Oct-23 Residual risk assessment performed, submitted for final approval and closure ~ 12-Sep-23 All actions complete and verified by treatment owner ~ 22-Aug-23 Cameras installed and verified by Treatment owner. Front desk host starts first week of Sep ~ 15-Jul-23 Contacted recruitor to hire front desk host, and contractor to install cameras. ~ 12-Jul-23 Met with stakholders to propose treatment plan. All agreed. Assigned treatment owner. |  | 2023-09-12 | 3 - Major ($1.5M - $3M, 10% - 20%) | 2 - Unlikely (11% - 40%) | 10 | $15M | 1 month from treatment completion date | 2023-10-12 | NA | Tom Jones, VP of Engineering Product Compliance
0 | A000 | Source Code THIS IS MEANT TO BE AN EXAMPLE - PLEASE UPDATE AS NECESSARY | 2023-07-12 | Mike Smith | C: Disclosure / exposure of source code, whether intentional or not, could lead to a confidentiality breach I: If the source code is accessed by a nefarious actor, the integrity of the source code could be compromised A: Inability to access source code would have impacts on day-to-day development and technical support operations all of the above could lead to delays in work/project completion, loss of revenue, resource impacts and increased vulnerabilites | Additional controls within Azure | 1 - Minor (<500K, <5%) | 2 - Unlikely (11% - 40%) | 2 | $5M |  | NA - Existing controls have been evaluated and found to be effective | Wayne Newton | NA | ~ 12-Jul-23 Inherent risk assessment indicates a risk ranking of low. Per the risk mgmgt process, this risk will be accpted with no mitigation/treatment |  | NA | 1 - Minor (<500K, <5%) | 2 - Unlikely (11% - 40%) | 2 | $5M | NA | NA | NA | NA
R010 |  | Internet facing Lab Hosts | 2015-02-03 | Amitraj Deb | As the lab network needs to be accessed from Internet, there is threat of attacking from out side | We have deployed Perimter firewall, to block the unwanted traffic and allow only required traffic. Also we have adopted geo filter to allow traffic from whitelisted countries(US, India only). Periodic scans are done for checking the new vulnerabilities and patched as per severity of the vulnerabilities. Is the Corporate network and business operation tools(JIRA, Confluence) isolated from this LAB? | 3 - Major ($1.5M - $3M, 10% - 20%) | 1 - Rare (<10%) | 5 |  | Accept/Approve | NA | NA | NA | 12/17/2025: Every 6mths (Q2, Q4 MR reviews). To check if bangalore hosts and lab is following the Global EIS and patching and monitoring. And all controls for montitoring are intact. And note any deviations which needs further mitigations | Monitoring | NA | 1 - Minor (<500K, <5%) | 2 - Unlikely (11% - 40%) | 2 |  | Every 6 Months | 2026-07-15 | 2021-03-10 | Amitraj Deb | 6Mths | Every 6mths (Q2, Q4 MR reviews). To check if bangalore hosts and lab is following the Global EIS and patching and monitoring. And all controls for montitoring are intact. And note any deviations which needs further mitigations
R011 |  | Protection of Lab Hosts | 2015-09-03 | Amitraj Deb | All the hosts are prone to attacks from internal network as well. Remove this one | We have deployed Host based intrusion Prevention system to secure the host from internal and external attacks | 1 - Minor (<500K, <5%) | 1 - Rare (<10%) | 1 |  | Accept/Approve | NA | NA | NA | 12/17/2025: Every 6mths (Q2, Q4 MR reviews). To check if bangalore hosts and lab is following the Global EIS and patching and monitoring. And all controls for montitoring are intact. And note any deviations which needs further mitigations | Monitoring | NA | 1 - Minor (<500K, <5%) | 1 - Rare (<10%) | 1 |  | Every 6 Months | 2026-07-15 | 2021-03-10 | Amitraj Deb | 6Mths | Every 6mths (Q2, Q4 MR reviews). To check if bangalore hosts and lab is following the Global EIS and patching and monitoring. And all controls for montitoring are intact. And note any deviations which needs further mitigations
R012 |  | Protection Of Lab Network | 2014-09-03 | Amitraj Deb | The network, and devices are prone to internal and external attacks | We have deployed Network based Intrusion Prevention System which is hueristic based. It identifies network patterns, and learns the traffic and allows only qualified traffic, and any new patterns or un qualified traffic will be blocked automatically and network administrator will be alerted through mail | 1 - Minor (<500K, <5%) | 1 - Rare (<10%) | 1 |  | Accept/Approve | NA | NA | NA | 12/17/2025: Every 6mths (Q2, Q4 MR reviews). To check if bangalore network and lab is following the Global EIS and patching and monitoring. And all controls for montitoring are intact. And note any deviations which needs further mitigations | Monitoring | NA | 1 - Minor (<500K, <5%) | 1 - Rare (<10%) | 1 |  | Every 6 Months | 2026-07-15 | 2021-03-08 | Amitraj Deb | Monitor | Every 6mths (Q2, Q4 MR reviews). To check if bangalore network and lab is following the Global EIS and patching and monitoring. And all controls for montitoring are intact. And note any deviations which needs further mitigations
R016 |  | Customer Support Tickets Data | 2021-02-22 |  | Unrecoverable loss of current customer support ticket snapshot from JSD | full database backup is taken daily and DR system is available(Active - Active) | 2 - Moderate ($500K - $1.5M, 5% - 10%) | 1 - Rare (<10%) | 3 |  | Accept/Approve | NA | NA | NA | 1/16/2026 from Jira Admin team>> The Atlassian Cloud is hosted on AWS infrastructure and uses automated Amazon RDS backups that are generated daily and retained for 30 days for point-in-time data restoration. Please refer to the following Atlassian Trust Center documentation in regards to backups: https://www.atlassian.com/trust/reliability/cloud-architecture-and-operational-practices#data-backups 12/17/2025: As the backup is taken care by MSI Global IT team and it is on a cloud Jira instance, IT and Atlassian are expected to provide high availability of data and backups to restore. Get confirmation from IT on the backup interval and backup duration | Treatment Implemented | NA | 1 - Minor (<500K, <5%) | 1 - Rare (<10%) | 1 |  | Not Needed | 2026-02-27 | 2021-03-08 | Ashwini Basavaraju | Not Needed | As the backup is taken care by MSI Global IT team and it is on a cloud Jira instance, IT and Atlassian are expected to provide high availability of data and backups to restore. Get confirmation from IT on the backup interval and backup duration
R024 | A006 | Defect Data | 2022-12-27 | Ashwini Basavaraju | Description / Threat: [Information Security] Locally hosted External ticketing tool is not accessible (https://servicedesk.kodiakptt.com) Gap: Redundancy of the tool not available | Notification will be sent to customers by the SRE team if there are any issues on the Service desk [external ticketing tool] so customers can report issues by email or call for ticket reporting | 1 - Minor (<500K, <5%) | 3 - Possible (41% - 60%) | 4 |  | Avoid/Prevent | This Tool will be migrated to either motorola service now or Moto jira in Q3 2023 [Sep] Q4 2023 [Dec] or Q1 2024 [Mar] | Ashwini Basavaraju | Q3 2024 [Sep] | 1/16/2026 from Jira Admin team>> The Atlassian Cloud is hosted on AWS infrastructure and uses automated Amazon RDS backups that are generated daily and retained for 30 days for point-in-time data restoration. Please refer to the following Atlassian Trust Center documentation in regards to backups: https://www.atlassian.com/trust/reliability/cloud-architecture-and-operational-practices#data-backups 11/26/2025: As the backup is taken care by MSI Global IT team and it is on a cloud Jira instance, IT and Atlassian are expected to provide high availability of data and backups to restore. Get confirmation from IT on the backup interval and backup duration. MOSES George Ashwini Basavaraju. 6/14/2024: Ashwini Basavarajuconfirmed JSD has been migrated to the cloud instance. Risk can be closed 4/12/2024: JSD under end of support, migration to cloud instance is being worked by MSI IT 1/16/2024: Migration from Jira service desk to service now has been pushed out further into 2024 QQ2/Q3. 10-Oct-23: As per IT Businees team, all stakeholders are part of the mailing list including the CMSO team group ID 06-Jul-2023: Migration to Service Now has been moved to Q4 2023 or Q1-2024. Any maintenance on the locally hosted JSD has to be informed beforehand by the local IT so that customers are kept informed. AI: Moses to check with Amitraj and Lakshmikanth 29-Mar-2023: Migration to Service Now has been planned to be done by Q2, onboarding to service now has begun. Status to be checked at end of Q2 and note if Risk can be closed if mirgation is complete. Backup to be checked for future reference 17-Jan-2023: Treatment to be followed up by Ashwinin in Q3 2023 service desk migration to global MSI Jira service desk plan. Residual risk to be evaluated if Global MSI Jira service desk has redundancy. | Treatment Implemented |  | 1 - Minor (<500K, <5%) | 2 - Unlikely (11% - 40%) | 2 |  | Not Needed | 2026-02-27 | 2024-06-14 | Ashwini Basavaraju | Not Needed | As the backup is taken care by MSI Global IT team and it is on a cloud Jira instance, IT and Atlassian are expected to provide high availability of data and backups to restore. Get confirmation from IT on the backup interval and backup duration
28 | A004 | Source Code Base (including Tests, Configuration, Pipelines) | 2023-04-24 | Anand Padmanabha | Description / Threat: [Information Security] GG TPS Artifact was down ==> Resulted in complete build and delivery was stalled. Hence identified GG TPS Artifact as Mission Critical Tier 1 Application for Product Delivery Occurrence, once in past 7-8 years Gap: Currently we have a dependency on Vendor Artifact http://www.gridgainsystems.com/nexus/content/repositories/external | Escalated to GG TPS Vendor And Vendor recovered the service within 2 hours | 2 - Moderate ($500K - $1.5M, 5% - 10%) | 1 - Rare (<10%) | 3 |  | Accept/Approve | 1. Incorporate into the local Artifact service, to remove the dependency on the Vendor for upcoming releases only (End of Q3-2023 onwards) 2. In case of recurrence before Q3. Design is planned to Migrate to local artifact for already delivered releases | Sanjeev Harohalli Upananda Singha | 2023-09-29 | 12/17/2025: Still a Low risk Issue has not recurred in past 2 years. And mitigation is to raise a vendor support when issue happens this is managed by EIS global team. MoM Attendees 2/19/2024: Christopher Poniecki, Sanjeev Harohalli Krishna Prasad M V Low risk, closed as there is existing compensation and no need pursue any further solutions/treatments. Comment by Christopher Poniecki 7:11 PM Yesterday @moses.george@motorolasolutions.com EIS GRC is recommending accepting the risk. It is deemed a LOW risk, as the likelihood is rare, and the impact is moderate. The team has a way to treat the risk by reaching out to the supplier directly via support. 2/16/2024: Mail sent to Kate and Adam, that the Risk will be closed as accepted if no further solution is given from MSI IT info security tea, [Vendor risk management team] by 2/23/2024 27-Sep MoM: Work with Vendor risk management team under Kate Woodsto identify if there is a solution or treatment that can be planned to overcome this Risk. Further discussions to follow after Kate speaks to her team and then connects someone from her team to work with UC Bangalore team Sanjeev Harohalliand Upananda Singha Attendees: Krishna Prasad M V Sanjeev Harohalli Upananda Singha Kate Woods Tony Bazdor 07-Jul-2023: Discussion done with Adam, Tony and KP. Adam said they will check if the rest of MSI are following some process or is this how we need to manage developement and accept the risk 04-Jul-2023: Maven dependencies as such, how are other MSI teams handling? Is there a public repo or MSI repo from where dev teams are pulling these files. To be checked with ISMS team who to contact to identify the mitigation plan. Action: KP, Moses to check with Adam/Tony | Residual/Current Risk Accepted | 2024-03-31 | 2 - Moderate ($500K - $1.5M, 5% - 10%) | 1 - Rare (<10%) | 3 |  | NA | NA | 2024-02-19 | Christopher Poniecki Sanjeev Harohalli | Not to monitor | Still a Low risk Issue has not recurred in past 2 years. And mitigation is to raise a vendor support when issue happens this is managed by EIS global team.
29 | NA | Human Resources DR site | 2023-11-20 | Venkat Venugopal | Description / Threat: [Operational Factors] Baroda site has stopped functioning, hence, no physical presence of Human Resources are available as a DR site at Baroda in order to support Bangalore site in case of any disaster at the Bangalore site where Human Resource support may get hindered and affect the Business continuity of UC from Bangalore. Gap: In case of a major disaster at the Bangalore site where employees cannot work from home as well, then the entire UC business will be affected. As there is NO DR site support for Human Resources. | Bangalore site can still function by adopting WFH in case of any shutdown of the Bangalore site Office due to any reason. Hence, human resource can still support the business coninuity even in the absence of Baroda site resources or unavailability of a office space. This has been proven to work during the COVID-19 scenario where over majority of the human resource where working from home and supporting the business at the Bangalore site. | 1 - Minor (<500K, <5%) | 1 - Rare (<10%) | 1 |  | Accept/Approve | Process improvement: Control to be implemented, Evidence to be shared on the security controls, hardening status and hotfixes applied on the Fresh VMs to IT team at the time of request public IPs. Check to be done at Dev for hardening as well as from IT that the evideces meet the security criteria. This has to be validated and shared to all Dev/Testing/Lab users/admins and stakeholders. Access control for new requests has to be routed through Manager for approval that all critical criterias from ISPMS are met 4/8/2024: Also, add regular patching and SOC 2 monitoring for these VMs. | Venkat Venugopal | 2024-03-30 | 12/17/2025: Kolkata site is supporting some of the UC R&D products partly. And we do not have a full human resource to support the entire product porfolio. This risk need not be monitored as human resource redundancy at any business unit will have its challenges of not being able to fully scale and replicate. So, closing this. However, onboarding Kolkata site to the ISPMS program and scope of audit needs to be tracked and planned 4/8/2024: Kolkata site onboarding is happening gradually to pick up dev and support work of UC Bangalore and share the workload. This could take a couple of qtrs. Maybe end of Q3'24. So, accepting the risk as risk rating is low and we can function still with WFH support which was effective during the pandemic time. To be discussed with site lead and management and update in the next MR meeting | Residual/Current Risk Accepted | 2024-03-30 | 1 - Minor (<500K, <5%) | 1 - Rare (<10%) | 1 |  | NA | 2024-04-08 | 2024-04-08 | Manjunatha Rajappa Venkat Venugopal | Not to monitor | Kolkata site is supporting some of the UC R&D products partly. And we do not have a full human resource to support the entire product porfolio. This risk need not be monitored as human resource redundancy at any business unit will have its challenges of not being able to fully scale and replicate. So, closing this. However, onboarding Kolkata site to the ISPMS program and scope of audit needs to be tracked and planned
30 | NA | NOC Room Functioning: Production System Access Tokens [Physical Devices], Test Handsets | 2023-12-23 | Ashwini Basavaraju | Description / Threat: [Operational Factors] In case of a power shutdown or facility shutdown, then the NOC restricted room will become Non Functional and inaccessible. Due to which the Access Tokens which is used for accessing the Production systems [Telstra, SFR, STCSC] will be prone to Risks. 1. Compromise of customer production system access in case the key is lost when moved outside the secure room 2. Loss of Business continuity as monitoring of Production system will not be possible Gaps: 1. If the physical token is used outside any unmonitored area or lost if the resource carrying the token compromises its safety, there could be Production system compormised or loss of data 2. If the personnel carrying the token is unavailable due to any emergency then token cannot be shared for accessing the customers systems. Hence, this could affect the business continuity at UC Bangalore if there is a need to access these customer systems for any kind of maintenance or upgrades or troubleshooting. 3. 24x7 monitoring of customer prod systems cannot be met as per SLA. due to planned site shutdown or fire drills | - WFH with 2 dedicated resources always being available with the access tokens - Unplanned incidents, communication is sent to customer on limited support till NOC functioning is brought up. | 3 - Major ($1.5M - $3M, 10% - 20%) | 2 - Unlikely (11% - 40%) | 10 |  | Avoid/Prevent | 2/16/2024: A service apartment or hotel room for NOC temp functioning can be planned. Once management approval is done this can be processed and process defined and documented to mitigate this risk. Action: Venkat Venugopaland Ashwini Basavaraju to work on this and own the process. ---------------------------------------------------------- 1. Power Backup to the NOC room in case of a power failure at the site OR 2. Secondary remote work enviornment for NOC, like, a temporary service apartment or work area Other treatments - Planned shutdown or fire drills should be communicated early to CMSO to arrange for the remote support backup environment to be setup at service apartment. - WFH during Covid was possible based on customer approval to support from WFH. However, managing hand over of the access tokens to different shift personnel becomes a logistical bottleneck as the keys are limited to one or max. 2 keys. CMSO to explore if customer approval can be taken again for WFH and additional tokens to be procured if customer agrees. | Venkat Venugopal Premdass Amaladass Ashwini Basavaraju | 2024-06-30 | 12/17/2025: The monitoring of customer systems, has moved to Penang. So risk to customer system monitoring is reduced from TSO Bangalore. Only L2 support and L3 offerred from here, which can be securely supported from WFH MSI policies. And also support can be prvided by setting temp L2/L3 support area at nearby work location in a MSI approved hotel room 6/13/2024: Ashwini Basavaraju CMSO lead is working with Admin and her team in working out the nuances of performing a mock drill and visit to the Service Apartment [DR location]. 5/9/2024: Reviewed with leadership Venkat Venugopal and Premdass Amaladass Ashwini Basavaraju Krishna Prasad M V. Mitigation accepted to utilize the service apartment already tied up with UC MSI Bangalore as a alternate location for NOC restricted room environment to be temporarily brought up. Service apartment needs - Availability of space and booking - Network - Power backup - Transport - Food & Water Ashwini Basavaraju will own the decision to switch to the alternate location in times of NOC room unusable/ inaccessible and document the process/SOP and point of contacts for this workflow. 4/12/2024: Venkat Venugopal Ashwini Basavaraju Premdass Amaladass Decision to be made on next action on enabling a alternate space. Meeting scheduled on 4/23/2024 1/8/2024: Mitigations to be discussed with risk managers and site leader on exploring a viable solution. As similar risk was present with the Penang team and they have the treatment in place already. PoC at Penang: SK Tang | Treatment Implemented | 2024-06-28 | 1 - Minor (<500K, <5%) | 2 - Unlikely (11% - 40%) | 2 |  | NA | 2024-06-14 | 2024-06-14 | Ashwini Basavaraju | Not to monitor | The monitoring of customer systems, has moved to Penang. So risk to customer system monitoring is reduced from TSO Bangalore. Only L2 support and L3 offerred from here, which can be securely supported from WFH MSI policies. And also support can be prvided by setting temp L2/L3 support area at nearby work location in a MSI approved hotel room
31 | A010 | Protection Of Lab Network | 2024-01-05 | Manjunatha Rajappa Amitraj Deb | Description / Threat:: [Information Security] LAB Virtual F5 setup environment [Fresh VM / Fresh VLAN - ON PREM] exposed to public without security hardening applied and hotfix not applied too by the install and upgrade dev team. Due to Partial MOP of F5 is followed and the steps for security hardening not applied and hotfix not applied in F5. Based on request from dev team, IT went ahead with Public IPs configured, and policy allowed to the fresh VLAN. Incident reported that F5 is exploited and exposed on 5-Jan by the Global security team. High risk not seen, as this is a Fresh VLAN. And on the F5 no virtual servers created or data loaded yet, so no data loss seen. It was like a black box and no access beyond the F5 virtual server allowed. Similarly, LAB Azure Env [New Setup] - If F5 created with external self IP with Public IP. This could lead to exploitation by external thereats. Gap: Process maturity, steps for security hardening not applied and hotfix not applied in new VM F5 or new VLAN configuration before exposing to the public network | Post the incident reported, initial mitigation The F5 VM that were exposed was delete | 1 - Minor (<500K, <5%) | 3 - Possible (41% - 60%) | 4 |  | Avoid/Prevent | Process improvement: Control to be implemented, Evidence to be shared on the security controls, hardening status and hotfixes applied on the Fresh VMs to IT team at the time of request public IPs. Check to be done at Dev for hardening as well as from IT that the evideces meet the security criteria. This has to be validated and shared to all Dev/Testing/Lab users/admins and stakeholders. Access control for new requests has to be routed through Manager for approval that all critical criterias from ISPMS are met 4/8/2024: Also, add regular patching and SOC 2 monitoring for these VMs. | Syed Nazir K Lakshmikanth Mannepalli Sunil Katke | 2025-01-31 | 11/26/2025: Monitoring has been enhanced by getting access to the google threat intelligence tool and Bangalore lab IT team is monitoring if any unpatched systems which are exposed to public n/w and flagging and taking mitigation steps to isolate and fix the gap. 9/25/2025: To be reviewed with IT manager and close if monitoring is done 7/7/2025: Still under monitoring to align some more dev teams, plan to review by end of Q3. Close by Q4 Lakshmikanth Mannepalli 1/9/2025: Inputs received from most of the teams, and IP details have been checked for public access and disabled. Need to review this risk with Syed Nazir K, Lakshmikanth Mannepalli, Amitraj Deb and close. 10/1/2024: IP list details are getting gathered by Lakshmikanth Mannepalli , mail sent to all teams. Expecting updates still from SQA, SII. Action Mahaveer Rajannavar Sai Rajesh Dittakavi. 7/24/2024: Syed Nazir K will work with Sunil Katke for Azure and Lakshmikanth Mannepalli for Lab/On Prem mgmt IP and external IP lists to monitor this weekly till this can be automated. This is to flag any F5 VM which has been exposed to the internet with external IP and disbale external access 4/22/2024: For LAB On-Prem and Azure on firewall/IT network can a control be put in place to have policy to only allow access to Management IP and External IP for F5 from local network and not accessible from Internet. 1. F5 UI Public IP(Self IP) should NOT be accessible from the Internet. 2. F5 Management IP should NOT be accessible from the Internet. 3. Check with F5 team to be kept in loop to confirm that latest version of patching is present on the F5 server. Please take these precautionary measures before provisioning the request. IT to document this as part of their checklist, communicate to IT team internally. Action: Lakshmikanth Mannepalli for On Prem env Sunil Katke for Azure env F5 team will have a note in the Qtrly patching email to highlight the need to apply the security hardening for fresh install/new setup. Action: Syed Nazir K Attendees: Syed Nazir K Lakshmikanth Mannepalli Amit Kumar Sunil Katke Once the above is in place and practiced, monitor and close the risk by end of Q2. 4/16/2024: Meeting scheduled on 4/22/2024 with the below stakeholders 2/9/2024: Process improvement to be discussed with Syed Nazir K Lakshmikanth Mannepalli Manjunatha Rajappa Amit Kumar Amitraj Deb | Monitoring | 2025-01-31 | 1 - Minor (<500K, <5%) | 1 - Rare (<10%) | 1 |  | Quarterly | 2026-03-16 | 2026-01-05 | Lakshmikanth Mannepalli Amitraj Deb | Monitor | Continue to monitor risk, so that process put in place is working and further monitoring enhancement can be put in plance based on global cybersecurity team
32 | A004 | Source Code Base (including Tests, Configuration, Pipelines) | 2024-01-02 | Amitraj Deb Suresh Thiriveedi | Description / Threat: [Source Code] NAS storage used for checkout and Dev build and code verification - A Sync issue to the storage from secondary storage [DR Bidadi site] to primary storage [primary site] led to source code commit not getting merged to the MAIN cloud GIT repo due to conflict, as the data backup that was synced from secondary to primary was outdated. - Media RV is using this as a mount point for dev validation. - Sync issue between Primary to secondary (Bidadi) for specific Media repo, Bidadi secondary went online for Media repo and pushed sync to Primary. - Sync from primary to secondary was stopped due b/w concerns from Jan-23, however, from Sep-23 sync was re-enabled with higher b/w of 100mbps. But, there will be a lag for very large storages which is taking more than 3 months to sync and still ongoing. - Windows security updates were applied during the annual DR test, and caused n/w mount point to become offline. - Loss of data due to old snapshot being synced from secondary to primary. Gap: - Dynamic sync of NAS storage from primary to DR site should not be disabled - Data snapshot backup in the DR site is outdated as sync of very large source code files is taking a week or more [at times months] - Security updates on the windows servers or VMs and ONTAP version could get outdated or are updated only at time of half yearly audit check for BCMS DR health check or annual DR test at the time of annual primary site facility / equipement maintenance. | - Sync from primary to secondary was stopped due b/w concerns from Jan-23, however, from Sep-23 sync was re-enabled with higher b/w of 100mbps. But, there will be a lag for very large storages which is taking more than 3 months to sync and still ongoing. - Windows security updates were applied during the annual DR test, and caused n/w mount point to become offline. | 3 - Major ($1.5M - $3M, 10% - 20%) | 3 - Possible (41% - 60%) | 15 |  | Avoid/Prevent | Mitigation Taken - Dynamic sync has been kept up and will not be disabled. - IT has changed the sync configuration to have a 7 days snapshot stored locally on the Primary and also sync to DR site. - As per the recommendation IT has upgraded both the Primary and Secondary systems to ONTAP 9.13.1.P3 from 9.9.1P2. - Additional trigger for email is configured to get alert that snapshot sync has been successful with status report. - Being monitored by vendor for some months also planned to have local trigger from IT team on the monitoring and status of the the VMs. | Lakshmikanth Mannepalli | 2024-03-31 | 12/17/2025: The issue has not recurred again. Only time sync gets stopped is for any planned maintenance. Patching to is regularly happening whenever there is a new patch. Risk level is still low. Backup data has been extended to 30 days of data. Hence, as confirmed by Lakshmikanth Mannepalli this risk does not need further monitoring 4/17/2024: Comfirmed by Suresh Thiriveedithat the mitigations taken are acceptable and we can close the risk with the current minotoring in place and residual risk rating 4/10/2024: Monitoring too is in place, daily email notification to IT owner indicating the system health and connectivity is in place. 2/9/2024: Check with IT team that all possible mitigation steps are in place and monitoring is happening with notification triggers. Post which check with Suresh Thiriveedi Soma Basu if the risk can be closed with the evidence shared by the IT team that the mitigation has been put in place 1/11/2024: Mitigation actions taken by IT, monitoring in progress. Monitor status to be checked in some weeks. Residual risk This scenario can repeat, however, loss of data is minimized as more frequent data backup has been setup with sync to DR site. There could be a 1 day to 2 day data loss in case this issue happens again as the backup and sync could be ongoing at the time of failure. Open Items Why only the media repo went offline is still unknown. | Residual/Current Risk Accepted | 2024-03-31 | 1 - Minor (<500K, <5%) | 2 - Unlikely (11% - 40%) | 2 |  | NA | 2024-04-17 | 2024-04-17 | Amitraj Deb Suresh Thiriveedi | Not to monitor | The issue has not recurred again. Only time sync gets stopped is for any planned maintenance. Patching to is regularly happening whenever there is a new patch. Risk level is still low. Backup data has been extended to 30 days of data. Hence, as confirmed by Lakshmikanth Mannepalli this risk does not need further monitoring
33 | NA | NOC Room Functioning: Production System Access and monitoring | 2024-01-27 | Ashwini Basavaraju | Description / Threat: In case of a Internet breakdown at the building/site or facility shutdown, then the NOC restricted room will not have data connectivity. Due to which the monitoring and access to Production systems will get blocked. Loss of Business continuity as monitoring of Production system will not be possible Gap: 1. WFH is possible, however, due to limited customer access token devices, managing its usage and circulating among the team becomes a logistical difficulty. Chances of misplacing or losing the tokens. 2. 24x7 monitoring of customer prod systems cannot be met as per SLA. due to planned site shutdown or fire drills or Internet outages which even affects mobile data and data cards/hotspots. Hence, this could affect the business continuity at UC Bangalore if there is a need to access these customer systems for any kind of maintenance or upgrades or troubleshooting. | - Planned shutdowns, WFH is possible, however, due to limited customer access token devices, managing its usage and circulating among the team becomes a logistical difficulty. Chances of misplacing or losing the tokens. - Unplanned incidents, communication is sent to customer on limited support till NOC functioning is brought up. | 3 - Major ($1.5M - $3M, 10% - 20%) | 2 - Unlikely (11% - 40%) | 10 |  | Avoid/Prevent | 2/16/2024: A service apartment or hotel room for NOC temp functioning can be planned. Once management approval is done this can be processed and process defined and documented to mitigate this risk. Action: Venkat Venugopaland Ashwini Basavaraju to work on this and own the process. Secondary remote work enviornment for NOC, like, a temporary service apartment or work area where WifI connectivity and ISP issues are minimal and functions 24x7 | Venkat Venugopal Premdass Amaladass Ashwini Basavaraju | 2024-06-30 | 12/17/2025: The monitoring of customer systems, has moved to Penang. So risk to customer system monitoring is reduced from TSO Bangalore. Only L2 support and L3 offerred from here, which can be securely supported from WFH MSI policies. And also support can be prvided by setting temp L2/L3 support area at nearby work location in a MSI approved hotel room 6/13/2024: Ashwini Basavaraju CMSO lead is working with Admin and her team in working out the nuances of performing a mock drill and visit to the Service Apartment [DR location]. 5/9/2024: Reviewed with leadership Venkat Venugopal and Premdass Amaladass [Admin], Ashwini Basavaraju [NOC area access manager], Krishna Prasad M V. [BCP lead]. Mitigation accepted to utilize the service apartment already tied up with UC MSI Bangalore as a alternate location for NOC restricted room environment to be temporarily brought up. Service apartment needs - Availability of space and booking - Network - Power backup - Transport - Food & Water Ashwini Basavarajuwill own the decision to switch to the alternate location in times of NOC room unusable/ inaccessible and coordinate the activity. And also document the process/SOP and point of contacts for this workflow and share with affected stakeholders. 4/12/2024: Venkat Venugopal Ashwini Basavaraju Premdass Amaladass Decision to be made on next action on enabling a alternate space. Meeting scheduled on 4/23/2024 2/14/2024: Mitigations to be discussed with risk managers and site leader on exploring a viable solution. As similar risk was present with the Penang team and they have the treatment in place already. PoC at Penang: SK Tang 06/14/2024 - Service apartment implementation is completed. | Treatment Implemented | 2024-06-28 | 1 - Minor (<500K, <5%) | 2 - Unlikely (11% - 40%) | 2 |  | NA | 2024-06-14 | 2024-06-14 | Ashwini Basavaraju | Not to monitor | The monitoring of customer systems, has moved to Penang. So risk to customer system monitoring is reduced from TSO Bangalore. Only L2 support and L3 offerred from here, which can be securely supported from WFH MSI policies. And also support can be prvided by setting temp L2/L3 support area at nearby work location in a MSI approved hotel room
R034 | NA | MSI Space in a shared Fourth Floor work space: Physical Access Controls and Surveilance Systems (New expanded space at Bangalore MFAR building in the same building as the 9th Floor) | 2026-04-10 | Aditya Saraf Prem Dass Amaladass Sridhara SV (CBRE) | The MSI dedicated space in the 4th floor is located within a shared 4th floor space. However the MSI space is having dedicated entry and exit with access controls designed by the Global MSI security and LPS teams in coordination with CBRE and UC Bangalore facility management. The access system and camera surveillance systems are not fully installed. Delayed - Was planned Feb, depends on hardware reaching Bangalore from customs. Access readers Surveillance camera systems. In absence of a MSI authorized access system and surveillance system, there is risk/threat of entry of non MSI personals, who may cause loss, damage to MSI resources, property, equipement and information assets. | A access controlled MAIN entry is provided by the vendor "Awfis" who owns and manages the 4th floor, that is manned by the vendor appointment guard and reception area. Anyone entering the 4th floor has to request access from the receptionist or security guard to open the MAIN door which can be unlocked by the access sysem controlled by the security guard from the reception. Access readers are present on the inside and not access enabled from the lobby leading from the lifts. Only after a verification by the security guard at the reception for a valid employee ID card who are authroized to use the 4th floor and a record of employee is registered in their access control system, are they allowed further beyond the reception area. Vistors too are supposed to validate their ID with a ID proof, along with details of the person they are visiting to meet at the 4th floor. Failure to meet this will lead to denial of further entry to the floor and the personal is escorted out the MAIN door of 4th floor. MSI employee or vistor who meets the verifiication criteria at the reception, are allowed to further move into the 4th floor. Visitors have to be escorted at all times by the visiting point of contact at the floor who has been validated already. A physical register too is placed to fill the employee and visitors details and ID information, with entry and exit times. The MSI space on the floor is a dedicated space just for MSI employees, access is restricted to anyone else. The space has a manned guard provided through MSI authorized vendor, currently provided under the approval of CBRE. Till the access readers and surveillance is put in place at 4th floor, the entry/exit is monitored by a MSI CBRE appointed guard. This is being reviewed weekly/monthly and renewed. Once the CBRE confirms the hardware for access and surveillance has been put in place and LPS has started monitoring. The manned guards will not be provided under CBRE. However, there is a review happening with the site operations lead and the management to bring in a 24x7 manned guard for the 4th floor too as part of the BU for UC. There is a physical log register maintained at the 4ht floor MSI space reception which is monitored by the guard, where employees have to enter their ID details with entry and exit times. Also a visitor register log is kept for visitors or vendors who are validated by ensuring a MSI employee or security guard escorts them at all times, as per the Global MSI policy for visitors/vendors who need to enter the facility for a valid business purpose. Risk to be monitored monthly to review progress on the access systems & the surveillance systems, and the guard needs. Low risk - As employees are not using it fully. And we have guards manning the entry and exit during the day. And after evening, employees are requested to move to 9th floor to continue to work if needed, and the 4th floor office space is kept locked physically during the late evening and night. | 1 - Minor (<500K, <5%) | 1 - Rare (<10%) | 1 |  | Mitigate/Reduce | Risk to be monitored monthly to review progress on the installation of the access systems & the surveillance systems, and the guard needs by site facility security manager, CBRE representative, site operations lead. And work towards ensuring the MSI access systems and surveillance systems are installed and monitoring begins at the earliest by MSI LPS team. | Aditya Saraf Prem Dass Amaladass Sridhara SV (CBRE) | 2026-05-31 | Treatment owners and target date to be reviewed monthly to note progress and change in action ownership if any | Treatment In Process | 2026-05-31 | 1 - Minor (<500K, <5%) | 1 - Rare (<10%) | 1 |  |  | 2026-05-08 |  | Aditya Saraf
R035 | NA | MSI Space in a shared Fourth Floor work space: Common server room shared by vendor and other tenants, houses MSI dedicated server rack that has only network switches for MSI network access. Physical Access Controls and Surveilance Systems (New expanded space at Bangalore MFAR building in the same building as the 9th Floor) | 2026-04-10 | Lakshmikanth Mannepalli | As the common server room located in 4th floor is not a MSI access controlled room, there is a possibility of bad actors gaining access to the MSI equipement and network. | The server room access is restricted and is access controlled by the floor admin (vendor/building owner). Only authorized person is allowed to enter the room after verification of identity at the MAIN entrance and reception. The person requesting access to the room has to enter their details in a physical log register specifically kept in the server room too, entry and exit times are recorded - The server rack, which currently holds MSI switches (no data stored), is controlled by a lock and key. - Access to the rack is restricted to MSI personnel, specifically Lakshmikanth Mannepalli who will be the access manager and controller of the physical key to the rack. - Access to the shared server room itself is controlled by the floor host/admin (Awfis) and requires presenting a valid company ID and request details, which are recorded in a log register. And the vendor floor admin will escort and accompany the person requesting access to the room, till the time of exit, and exit details is made in the log register - Vendor Access: When vendors are coming, Lakshmikanth Mannepalli will authorize the access and ensure MSI security guard or MSI access manager accompany the vendor to the server room. Where each persons details are entered in the vendor maintained server log register. - Internal Access (IT Team): Lakshmikanth Mannepalli will authorize the access and ensure MSI security guard or MSI access manager accompany the MSI employee to the server room. Where each persons details are entered in the vendor maintained server log register - Access Manager Change: Any change in the access manager's role must be recorded in the https://docs.googBangalore - Information Assets Dev Tools & It's Access Management Record and officially communicated via email to impacted stakeholders (Reporting manager, Site operations, site lead, ISPMS lead) - The room is under 24/7 CCTV surveillance, managed by the floor vendor. - The conduits carrying data cables are secured with metal casings. | 1 - Minor (<500K, <5%) | 1 - Rare (<10%) | 1 |  | TBD | Risk to be reviewed further with Lakshmikanth Mannepalli and Site Opertations team for any further mitigations or changes. | Lakshmikanth Mannepalli | 2026-05-31 | Risk to be reviewed further with Lakshmikanth Mannepalli and Site Opertations team for any further mitigations or changes. | Under Assessment | 2026-05-31 | 1 - Minor (<500K, <5%) | 1 - Rare (<10%) | 1 |  |  |  |  | Lakshmikanth Mannepalli

## Key terms
Category | Term | Definition
Step 1. Risk Identification | Risk I.D. | Designated I.D. Number of the identified risk
| Corresponding Information Asset I.D. / Link | Designated I.D. Number of the information asset for which the risk was identified. (if applicable)
| Asset | The specific asset or component that is being evaluated for threats, and vulnerabilites against risk. The specific area(s) and scope to which the risk applies. This may include informational assets, site locations, people, organizations, customers, equipment and systems, and so on.
| Date Risk Identified | The date the risk was first identified
| Risk Owner | The Risk Owner is the person(s) with the accountability and authority to oversee the disposition of a risk. They have the authority to formally assume responsibility for operating a system or program at an acceptable level of risk. The risk owner is responsible for budget oversight and/or the business operations supported by the system. This will generally be someone at the managerial level or higher. The Risk Owner is generally not involved in actual risk treatment; however, they retain accountability for the treatment of the reported risk, risk acceptance, approval of Current/Residual Risk, and closure.
| Risk Description; Threat/Vulnerability Summary w/ Potential Effect | A detailed explanation of the risk(s) that the asset or risk-source faces, including a summary of the threats and vulnerabilities that could be exploited to cause harm or damage, as well as an assessment of the potential impact or effect of those risks. The description should be clear, complete, and concise.
| Existing Mitigating Controls / Policies | The mitigation controls currently in place to address the threats to the asset or risk-source. And ISMS policies that specifically address the asset protection requirments
Step 2. Risk Assessment Refer to the "Risk Guide" tab | Inherent Impact | An estimate of the maximum expectation of loss the business would sustain as a result of a risk being realized; 1. given the existing set of controls, which may be incomplete or less than ideal. OR 2. given the complete absence of any mitigating controls. It is the overall effect, including financial, that the threat will cause if it occurs. Impact can relate directly to financial costs but may also include other factors such as loss of Confidentiality, Integrity or Availability (CIA) or of functionality, damage to reputation, legal, health and safety, security and environmental impacts.
| Inherent Likelihood | An estimate of the probability (or Likelihood) that a risk will manifest and become a problem; 1. given the existing set of controls, which may be incomplete or less than ideal. OR 2. given the complete absence of any mitigating controls. Likelihood is determined based on all currently available data, including past history, if applicable, and educated forecasting. "Risk Likelihood" is used in conjunction with "Risk Impact" to calculate "Risk Exposure". Likelihood is expressed quantitatively; the measurable %, or actual likelihood of something happening; by time or event (once every week, once every 3rd iteration, 20% of the time given a specific scenario).
| Inherent Risk Ranking | A rating determination based on the calculation; Inherent Impact (x) Inherent Likelihood = Inherent Risk Ranking. The ranking is determined using a matrix that enables sorting and prioritization of the risks within the register. The 5x5 risk matrix visualizes the relationship between likelihood and impact. There are four possible risk ratings; Low, Medium, High, Extreme. The matrix is further broken down by numerical values within each cell in the risk matrix (1-25) allow the ranking and prioritization of risks even if they fall within the same general risk rating categories of Low, Medium, High, Extreme.
| Inherent Financial impact | An estimate of the maximum expectation of loss, as expressed in financial terms, that the business would sustain as a result of a risk being realized. This is an estimate of the risk impacted cost/dollar amount that the risk will incur to the business or customer if not mitigated or controlled.
Step 3: Risk Response/Treatment | Treatment Decision | The treatment decision indicates the appropriate response/treatment to the reported risk. The possible Risk responses are: ■ Mitigate/Reduce ■ Accept/Approve ■ Transfer ■ Avoid/Prevent ■ Contingency/Compensate
| Treatment Plan / Controls To Be Implemented | Clear, complete and concise details of the mechanisms or "plan" that will be implemented to mitigate the risk, as supported by the treatment decision.
| Treatment Owner (Name) | The treatment owner is the individual responsible for owning the entirety of the remediation/mitigation process for assigned risks. This includes, but is not limited to remediation/mitigation planning & tracking, timeline creation, presentations to management, task assignment, cost-benefit analyses, control effectiveness analyses, etc. This could be someone at any level, due to the nature of risk treatments. The person with the knowledge, skills and experience to mitigate a risk. Responsible for assigned risks, determine the best course of action in treatment, and to develop and implement plans to mitigate the risk.
| Treatment Target completion date | The estimated date when the treatment plan / controls will be implemented and marked as complete.
| Treatment Update / Progress | An ongoing and updated record or history on the progress of the treatments plans implimentation. The status should be noted with an entry date and written with clear, complete and concise details and ongoing and current status of the mitigation plan and risk threat. This should be kept updated with any significant changes to the plan or risk.
| Treatment status | The current, and updated status of the treatment plan. The possible treatment status selections are: ■ Under Assessment ■ Treatment Identified ■ Treatment In Process ■ Treatment Implemented ■ Monitoring ■ Residual/Current Risk Accepted
| Treatment Completion Date | The actual date when the treatment plan / controls were implemented and marked as complete.
| Residual / Current Impact | The Residual / Current Risk impact estimate of the maximum expectation of loss the business would sustain as a result of a risk being realized, based on the portion of risk remaining after risk treatment has been applied, and represents the current level of risk. In scenarios where any risk treatment has yet to be performed, this is the same as inherent risk. When some level of treatment has been applied, the current risk will typically be lower than the inherent risk.
| Residual / Current Likelihood | The Residual / Current Risk likelihood estimate of the probability (or Likelihood) that a risk will manifest and become a problem; based on the portion of risk remaining after risk treatment has been applied, and represents the current level of risk. In scenarios where any risk treatment has yet to be performed, this is the same as inherent risk. When some level of treatment has been applied, the current risk will typically be lower than the inherent risk.
| Residual / Current Risk Level | The Residual / Current Risk Level rating based on the calculation; Residual Impact (x) Residual Likelihood = Residual / Current Risk Ranking. The ranking is determined using a matrix that enables sorting and prioritization of the risks within the register. The 5x5 risk matrix visualizes the relationship between likelihood and impact. There are four possible risk ratings; Low, Medium, High, Extreme. The matrix is further broken down by numerical values within each cell in the risk matrix (1-25) allow the ranking and prioritization of risks even if they fall within the same general risk rating categories of Low, Medium, High, Extreme.
| Residual / Current Financial Impact | The Residual / Current estimate of the maximum expectation of loss, as expressed in financial terms, that the business would sustain as a result of a risk being realized. This is an estimate of the cost/dollar amount to the business or customer as calculated after the treatment plan / controls have been implimented.
Step 4: Risk Monitoring / Closure | Monitoring Cadence | Monitoring cadence as a risk response implies that the risk ranking has been lowered to an acceptable risk level or has been accepted, i.e. the risk is no longer being actively managed, but will be reassessed for a specific timeframe or at designated intervals to ensure that the current controls are still effective in maintaining the residual / current risk level or ranking. This may be by time or event (ie. once every month, once every 3rd iteration, 20% of the time given a specific scenario) or at one or more specific future dates, or time frame.
| Next Review Date | Next Review Date refers to the date on which the risk will be reviewed or evaluated to ensure that it is up-to-date and relevant. This date is usually set in advance by the Treatment Owner, and serves as a reminder to initiate a review or update. The purpose of a Next Review Date is to ensure that risk process information remains accurate and current.
| Closure Date | The specific date that the residual / current risk was accepted and risk closure was approved.
| Risk Owner & Title | Name and title of the risk owner or individual that approved the acceptance of the residual / current risk ranking and risk closure. Residual Risks must be reviewed and accepted by the appropriate risk owner based on the "Inherent Risk Exposure Rating" prior to closing the risk.

## Risk Assessment Guide
Likelihood of Occurrence | Almost Certain | Medium (7) | High (14) | Extreme (20) | Extreme (22 | Extreme (25)
| Likely | Medium (6) | High (13) | High (16) | Extreme (21) | Extreme (24)
| Possible | Low (4) | Medium (9) | High (15) | High (18) | Extreme (23)
| Unlikely | Low (2) | Medium (8) | Medium (10) | High (17) | High (19)
| Rare | Low (1) | Low (3) | Low (5) | Medium (11) | Medium (12)
|  | 1 | 2 | 3 | 4 | 5
|  | Minor | Moderate | Major | Severe | Catastrophic
IMPACT
SITE LEVEL RISK IMPACT - Definitions and Directional Guidance
| Descriptor | Level | Description |  |  |  | Financial Impact*
| Minor | 1 | A risk event that, if it occurs, will have a minor impact on defined objectives or the identified areas of concern. Oversight required to ensure risk remains low. Little to no financial impact/loss or potential damage to business factors. Management, mitigation and reporting is generally at the site/project level. |  |  |  | <$500k <5%
| Moderate | 2 | A risk event that, if it occurs, will have a moderate impact and noticeable effect on defined objectives or the identified areas of concern. Mitigation actions to be determined and prioritized with other risks Potential financial impact/loss or potential damage to business factors Management, mitigation and reporting is generally at the site/project level. |  |  |  | $500K - $1.5M 5% - 10%
| Major | 3 | A risk event that, if it occurs, will have a major impact and detrimental effect on objectives or the identified areas of concern. Mitigation actions to be determined and immediately prioritized Major financial impact/loss or potential damage to business factors Management, mitigation and reporting is generally at the site/project level. |  |  |  | $1.5M - $3M 10% - 20%
| Severe | 4 | A risk event that, if it occurs, will have a severe impact and detrimental effect on objectives or the identified areas of concern. Severe impact imminent - Immediate escalation, mitigation review and risk management required Major financial impact/loss or potential damage to business factors Management and mitigation may be at the site/project, regional or global level. Reporting is escalated to the regional level |  |  |  | $3M - $10M 20% - 30%
| Catastrophic | 5 | A risk event that, if it occurs, will have a catastrophic impact and detrimental effect on objectives or the identified areas of concern. Catastrophic impact imminent - Immediate escalation, mitigation review and risk management required Grave financial impact/loss or potential damage to business factors Management and mitigation may be at the site/project, regional or global level. Reporting is escalated as appropriate |  |  |  | >$10M >30%
CORPORATE LEVEL RISK IMPACT - Definitions and Directional Guidance
| Descriptor | Level | Description |  |  |  | Financial Impact*
| Minor | 1 | - A recordable injury or - Consequences can be absorbed under normal operating conditionsor - Potential impact to brand and reputation, and key constituent confidenceor - Requires senior and middle management attention |  |  |  | <$5M
| Moderate | 2 | - Operational < 1 week 100% shutdown or - Reputation, community / media attention for 1-2 daysor - Legal, some commercial or legal non-complianceor - Requires senior and middle management attention, Board of Directors notified |  |  |  | $5M - $15M
| Major | 3 | - Operational > 1 week 100% shutdown or - Key constituent confidence, reputation is damaged, adverse publicity on a regional basisor - Legal, serious breach of contract or lawor - Requires Board of Directors attention and immediate senior management |  |  |  | $15M - $30M
| Severe | 4 | Requires immediate attention of Board of Directors and senior management and one of the following: - Operational 1 month 100% shutdown or - Legal, major breach of contract or lawor - Reputation is damaged on a global basis |  |  |  | $30M - $100M
| Catastrophic | 5 | Requires immediate attention of Board of Directors and senior management and one of the following: - Operational >1 month 100% shutdown or - Reputation is damaged on a long term, global basis |  |  |  | >$100M
RISK LIKELIHOOD - Definitions and Directional Guidance
| Descriptor | Level | Description |  |  |  | Financial Impact*
| Rare | 1 | The future risk event may occur only in exceptional circumstances |  |  |  | <10%
| Unlikely | 2 | The chance of the future risk event is not expected but may occur |  |  |  | 11% - 40%
| Possible | 3 | The chance of a future risk event in this area is more than remote but less than likely |  |  |  | 41% - 60%
| Likely | 4 | A future risk event in this area is likely to occur |  |  |  | 61% - 90%
| Almost Certain | 5 | A future risk event in this area is almost certain to occur |  |  |  | >90%
Information Security Risk thought starters
Building security
Communications
Complex legacy environment
Cyber threats
Defects or system issues
Employee dissatisfaction
Enterprise impact
Improper funding/staffing
Internet/Intranet
Malicious attacks
Master data integrity
On-boarding new employees
Operations
Organizational change management
Proprietary information
Viruses

## Risk Process Guide
Risk Process Guide
The guidance provided in this section supports the "MSI Common Risk Management Framework", and the "MSI Common Risk Management Framework: ISO 27000 Series Program Appendix V2.0" It is meant to provide general guidance to supplement the framework's contents. Risk process deviations to accommodate business needs should be logged in this template or other process documentation to provide a reference for audits or other requirements.
General | While the template's fields are not labeled as mandatory, consideration should be given to completing all applicable fields, as required by the risk program being followed, as well as any other requirements as mandated through frameworks, compliance standards, or business unit practices for which the risk program is supporting.
Risk/Context Identification | Risk identification starts with establishing the context of the risk including; the impacted scope, asset, threat and/or vulnerability (considering the CIA triad), existing controls, and related policies where applicable.
~ A clear, complete, and concise description of the actual identified risk should be documented which includes the potential effect should the risk manifest into a problem. Enough detail should be documented to provide for a complete understanding of the threat, vulnerability and potential effect or impact.
Risk assessment / Rating the risk | A risk assessment is performed to determine the inherent risk, which is the risk rating or level given the existing set of controls, which may be incomplete or less than ideal. If applicable to business needs: Inherent risk may also be assessed on the level of raw or untreated risk; that is, the natural level of risk inherent in a process or activity without doing anything to reduce the likelihood or mitigate the severity of a mishap, or the amount of risk.
~ The risk assessment guide should be used when rating the risk. The assessor should consider available quantitative and qualitative data as well as draw on historical information, and subject matter experts when available.
Risk Acceptance | Risk acceptance is the appropriate risk response when the identified risk is within the organizational risk tolerance. Organizations can accept risk deemed to be low, moderate, or high depending on particular situations or conditions. Risk acceptance can occur without risk treatment or during the process of risk treatment. Accepted risks are subject to monitoring and review.
~ The guidance for risk acceptance is to accept any risk with a risk rating of low, and to pursue further evaluation and potential treatment/mitigation for any risk that is rated as medium or higher. Further criteria around risk acceptance can be found in the MSI Common Risk Management Framework and relevant organization specific Risk Management Framework Appendices
Risk Response/Treatment | Risk Treatment is the process of selecting and implementing measures to modify risk. The treatment decision indicates the appropriate response/treatment to the reported risk. The possible Risk responses are: ■ Mitigate/Reduce ■ Accept/Approve ■ Transfer ■ Avoid/Prevent ■ Contingency/Compensate When identifying risk treatment options the primary goal is to avoid/prevent risk. If this is not possible, you should look to reduce the likelihood, impact or both. Remember; there may be a cost associated with each treatment plan.
~ One or multiple treatment options can be determined along with the specific controls to be implemented for each treatment option. A Treatment Owner should also be determined. The treatment owner is the individual responsible for owning the entirety of the remediation/mitigation process for assigned risks.
~ The Residual Risk section of the template allows for further tracking on treatment plans and provides for the determination of Residual Risk (Current risk after mitigation).
Risk approval | The risk approval process is implemented once a final risk disposition is determined. This may include accepting the risk or the implementation of treatment(s). The risk owner has the responsibility for review and approval of the final risk disposition. The treatment and risk owner responsibilities may be assigned to the same individual based on business needs. The risk owner may delegate responsibilities as appropriate.
~ Risk acceptance of low rated risks may be closed or deferred for monitoring without formal risk owner approval. Formal risk approval/sign-off should be documented for risks rated medium or higher.
Monitoring and Closure | Monitoring as a risk response implies that the risk ranking has been lowered to an acceptable risk level or has been accepted, i.e. the risk is no longer being actively managed, but will be reassessed for a specific timeframe or at designated intervals to ensure that the current controls are still effective in maintaining the residual / current risk level or ranking. This may be by time or event (ie. once every month, once every 3rd iteration, 20% of the time given a specific scenario) or at one or more specific future dates, or time frame.
~ A risk may be closed once an acceptable monitoring period has been completed, or if it has been determined that there is no longer a threat to the asset. The risk accept/approval process should be followed for risks that are to be closed. See section 7. Risk Accept/Approve
NOTE: | Please refer to the "MSI Common Risk Management Framework", and the "MSI Common Risk Management Framework: ISO 27000 Series Program Appendix V2.0" for more information.

## Selection Data ( ADMIN ONLY ) (hidden)
Risk Selections | (pswd - Register1) | [6 empty] | Risk Assessment |  | Clause Or Control #
Risk Category | Impact | Probability | Risk Level | Treatment | Treatment Status | Asset Type (in progress) | Threats | Impact X Probability | Risk | ISO 27001 - Clause - 4 Context of the organization
Business Factors | 5 - Catastrophic (>$10M, >30%) | 5 - Almost Certain (<90%) | Extreme | Accept/Approve | Under Assessment | Procedure | Loss of capability | 1 - Minor (<500K, <5%) X 1 - Rare (<10%) | 1 | ISO 27001 - Clause - 4.1 Understanding the organization and its context
Information Security | 4 - Severe ($3M - $10M, 20% - 30%) | 4 - Likely (61% - 90%) | High | Mitigate/Reduce | Treatment Identified | Primary Information | Physical Human Harm | 1 - Minor (<500K, <5%) X 2 - Unlikely (11% - 40%) | 2 | ISO 27001 - Clause - 4.2 Understanding the needs and expectations of interested parties
Operational Factors | 3 - Major ($1.5M - $3M, 10% - 20%) | 3 - Possible (41% - 60%) | Medium | Transfer | Treatment In Process | Documents/Reports | Compromise of Information | 1 - Minor (<500K, <5%) X 3 - Possible (41% - 60%) | 4 | ISO 27001 - Clause - 4.3 Determining the scope of the ISMS
| 2 - Moderate ($500K - $1.5M, 5% - 10%) | 2 - Unlikely (11% - 40%) | Low | Avoid/Prevent | Treatment Implemented | Email | Multiple | 1 - Minor (<500K, <5%) X 4 - Likely (61% - 90%) | 6 | ISO 27001 - Clause - 4.4 ISMS
| 1 - Minor (<500K, <5%) | 1 - Rare (<10%) |  | Contingency/Compensate | Monitoring | Application |  | 1 - Minor (<500K, <5%) X 5 - Almost Certain (<90%) | 7 | ISO 27001 - Clause - 5 Leadership
|  |  |  | TBD | Residual/Current Risk Accepted
[6 empty] | Database |  | 2 - Moderate ($500K - $1.5M, 5% - 10%) X 1 - Rare (<10%) | 3 | ISO 27001 - Clause - 5.1 Leadership and commitments
[6 empty] | Customer PII |  | 2 - Moderate ($500K - $1.5M, 5% - 10%) X 2 - Unlikely (11% - 40%) | 8 | ISO 27001 - Clause - 5.2 Policy
[6 empty] | Fixed Equipment |  | 2 - Moderate ($500K - $1.5M, 5% - 10%) X 3 - Possible (41% - 60%) | 9 | ISO 27001 - Clause - 5.3 Organisational roles, responsibilities and authorities
[6 empty] | Customer operational data |  | 2 - Moderate ($500K - $1.5M, 5% - 10%) X 4 - Likely (61% - 90%) | 13 | ISO 27001 - Clause - 6 Planning
[6 empty] | Electronic Media |  | 2 - Moderate ($500K - $1.5M, 5% - 10%) X 5 - Almost Certain (<90%) | 14 | ISO 27001 - Clause - 6.1 Actions to address risks and opportunities
[6 empty] | Printed Media |  | 3 - Major ($1.5M - $3M, 10% - 20%) X 1 - Rare (<10%) | 5 | ISO 27001 - Clause - 6.1.1 General
[6 empty] | Software |  | 3 - Major ($1.5M - $3M, 10% - 20%) X 2 - Unlikely (11% - 40%) | 10 | ISO 27001 - Clause - 6.1.2 Information security risk assessment
[6 empty] | IT Network |  | 3 - Major ($1.5M - $3M, 10% - 20%) X 3 - Possible (41% - 60%) | 15 | ISO 27001 - Clause - 6.1.3 Information security risk treatment
[6 empty] | Personnel |  | 3 - Major ($1.5M - $3M, 10% - 20%) X 4 - Likely (61% - 90%) | 16 | ISO 27001 - Clause - 6.2 Information security objectives and planning to achieve them
[6 empty] | Facility /building |  | 3 - Major ($1.5M - $3M, 10% - 20%) X 5 - Almost Certain (<90%) | 20 | ISO 27001 - Clause - 7 Support
[6 empty] | Communications |  | 4 - Severe ($3M - $10M, 20% - 30%) X 1 - Rare (<10%) | 11 | ISO 27001 - Clause - 7.1 Resources
[6 empty] | Utility |  | 4 - Severe ($3M - $10M, 20% - 30%) X 2 - Unlikely (11% - 40%) | 17 | ISO 27001 - Clause - 7.2 Competence
[6 empty] | Customer |  | 4 - Severe ($3M - $10M, 20% - 30%) X 3 - Possible (41% - 60%) | 18 | ISO 27001 - Clause - 7.3 Awareness
[6 empty] | Supplier /Vendor |  | 4 - Severe ($3M - $10M, 20% - 30%) X 4 - Likely (61% - 90%) | 21 | ISO 27001 - Clause - 7.4 Communication
[6 empty] | Internal Org |  | 4 - Severe ($3M - $10M, 20% - 30%) X 5 - Almost Certain (<90%) | 22 | ISO 27001 - Clause - 7.5 Documented information
[6 empty] | Mobile Equipment |  | 5 - Catastrophic (>$10M, >30%) X 1 - Rare (<10%) | 12 | ISO 27001 - Clause - 7.5.1 General
[6 empty] | Other |  | 5 - Catastrophic (>$10M, >30%) X 2 - Unlikely (11% - 40%) | 19 | ISO 27001 - Clause - 7.5.2 Creating and updating
[8 empty] | 5 - Catastrophic (>$10M, >30%) X 3 - Possible (41% - 60%) | 23 | ISO 27001 - Clause - 7.5.3 Control of documented information
[6 empty] | Procedures |  | 5 - Catastrophic (>$10M, >30%) X 4 - Likely (61% - 90%) | 24 | ISO 27001 - Clause - 8 Operation
[6 empty] | Primary Information |  | 5 - Catastrophic (>$10M, >30%) X 5 - Almost Certain (<90%) | 25 | ISO 27001 - Clause - 8.1 Operation planning and control
[6 empty] | Supporting IT Systems, Tools and Data Processing Facilities |  |  |  | ISO 27001 - Clause - 8.2 Information security risk assessment
[6 empty] | Transportable Equipment |  |  |  | ISO 27001 - Clause - 8.3 Information security risk treatment
[6 empty] | Fixed Equipment |  |  |  | ISO 27001 - Clause - 9 Performance Evaluation
[6 empty] | Processing peripherals |  |  |  | ISO 27001 - Clause - 9.1 Monitoring, measurement, analysis and evaluation
[6 empty] | Electronic medium |  |  |  | ISO 27001 - Clause - 9.2 Internal audit
[6 empty] | Other media |  |  |  | ISO 27001 - Clause - 9.3 Management review
[6 empty] | Software - operating system |  |  |  | ISO 27001 - Clause - 10 Improvement
[6 empty] | Software - service maintenance or administration |  |  |  | ISO 27001 - Clause - 10.1 Nonconformity and corrective action
[6 empty] | Software - standard business application |  |  |  | ISO 27001 - Clause - 10.2 Continual Improvement
[6 empty] | Software - specific business application |  |  |  | ISO 27001 - Control - A5 Information security policies
[6 empty] | Network - medium and supports |  |  |  | ISO 27001 - Control - A5.1 Management direction for information security
[6 empty] | Network - passive or active relay |  |  |  | ISO 27001 - Control - A5.1.1 Policies for information security
[6 empty] | Personnel - decision makers |  |  |  | ISO 27001 - Control - A5.1.2 Review of the policies for information security
[6 empty] | Personnel - Operation/Maintenance |  |  |  | ISO 27001 - Control - A6 Organization of information security
[6 empty] | Location - External Environment |  |  |  | ISO 27001 - Control - A6.1 Internal organization
[6 empty] | Location - East Burwood Premises |  |  |  | ISO 27001 - Control - A6.1.1 Information security roles and responsibilities
[6 empty] | Location - NOCC Zone |  |  |  | ISO 27001 - Control - A6.1.2 Segregation of duties
[6 empty] | Location - Communications |  |  |  | ISO 27001 - Control - A6.1.3 Contact with authorities
[6 empty] | Location - Utilities |  |  |  | ISO 27001 - Control - A6.1.4 Contact with special interest groups
[6 empty] | Organisation - Authorities and Customers |  |  |  | ISO 27001 - Control - A6.1.5 Information security in project management
[6 empty] | Organisation - Structure and Supporting Services |  |  |  | ISO 27001 - Control - A6.2 Mobile devices and teleworking
[6 empty] | Organisation - Project or System |  |  |  | ISO 27001 - Control - A6.2.1 Mobile device policy
[6 empty] | Organisation - Subcontractors or Suppliers or Customers |  |  |  | ISO 27001 - Control - A6.2.2 Teleworking
ISO 27001 - Control - A7 Human resource security
ISO 27001 - Control - A7.1 Prior to employment
ISO 27001 - Control - A7.1.1 Screening
ISO 27001 - Control - A7.1.2 Terms and conditions of employment
ISO 27001 - Control - A7.2 During employment
ISO 27001 - Control - A7.2.1 Management responsibilities
ISO 27001 - Control - A7.2.2 Information security awareness, education and training
ISO 27001 - Control - A7.2.3 Disciplinary process
ISO 27001 - Control - A7.3 Termination and change of employment
ISO 27001 - Control - A7.3.1 Termination or change of employment responsibilities
ISO 27001 - Control - A8 Asset management
ISO 27001 - Control - A8.1 Responsibility for assets
ISO 27001 - Control - A8.1.1 Inventory of assets
ISO 27001 - Control - A8.1.2 Ownership of assets
ISO 27001 - Control - A8.1.3 Acceptable use of assets
ISO 27001 - Control - A8.1.4 Return of assets
ISO 27001 - Control - A8.2 Information classification
ISO 27001 - Control - A8.2.1 Classification of information
ISO 27001 - Control - A8.2.2 Labelling of information
ISO 27001 - Control - A8.2.3 Handling of assets
ISO 27001 - Control - A8.3 Media handling
ISO 27001 - Control - A8.3.1 Management of removable media
ISO 27001 - Control - A8.3.2 Disposal of media
ISO 27001 - Control - A8.3.3 Physical media transfer
ISO 27001 - Control - A9 Access control
ISO 27001 - Control - A9.1 Business requirements of access control
ISO 27001 - Control - A9.1.1 Access control policy
ISO 27001 - Control - A9.1.2 Access to networks and network services
ISO 27001 - Control - A9.2 User access management
ISO 27001 - Control - A9.2.1 User registration and de-registration
ISO 27001 - Control - A9.2.2 User access provisioning
ISO 27001 - Control - A9.2.3 Management of privileged access rights
ISO 27001 - Control - A9.2.4 Management of secret authentication information of users
ISO 27001 - Control - A9.2.5 Review of user access rights
ISO 27001 - Control - A9.2.6 Removal or adjustment of access rights
ISO 27001 - Control - A9.3 User responsibilities
ISO 27001 - Control - A9.3.1 Use of secret authentication information
ISO 27001 - Control - A9.4 System and application access control
ISO 27001 - Control - A9.4.1 Information access restriction
ISO 27001 - Control - A9.4.2 Secure log-on procedures
ISO 27001 - Control - A9.4.3 Password management system
ISO 27001 - Control - A9.4.4 Use of privileged utility programs
ISO 27001 - Control - A9.4.5 Access control to program source code
ISO 27001 - Control - A10 Cryptography
ISO 27001 - Control - A10.1 Cryptographic controls
ISO 27001 - Control - A10.1.1 Policy on the use of cryptographic controls
ISO 27001 - Control - A10.1.2 Key management
ISO 27001 - Control - A11 Physical and environmental security
ISO 27001 - Control - A11.1 Secure areas
ISO 27001 - Control - A11.1.1 Physical security perimeter
ISO 27001 - Control - A11.1.2 Physical entry controls
ISO 27001 - Control - A11.1.3 Securing offices, rooms and facilities
ISO 27001 - Control - A11.1.4 Protecting against external and environmental threats
ISO 27001 - Control - A11.1.5 Working in secure areas
ISO 27001 - Control - A11.1.6 Delivery and loading areas
ISO 27001 - Control - A11.2 Equipment
ISO 27001 - Control - A11.2.1 Equipment siting and protection
ISO 27001 - Control - A11.2.2 Supporting utilities
ISO 27001 - Control - A11.2.3 Cabling security
ISO 27001 - Control - A11.2.4 Equipment maintenance
ISO 27001 - Control - A11.2.5 Removal of assets
ISO 27001 - Control - A11.2.6 Security of equipment and assets off-premises
ISO 27001 - Control - A11.2.7 Secure disposal or reuse of equipment
ISO 27001 - Control - A11.2.8 Unattended user equipment
ISO 27001 - Control - A11.2.9 Clear desk and clear screen policy
ISO 27001 - Control - A12 Operations security
ISO 27001 - Control - A12.1 Operational procedures and responsibilities
ISO 27001 - Control - A12.1.1 Documented operating procedures
ISO 27001 - Control - A12.1.2 Change management
ISO 27001 - Control - A12.1.3 Capacity management
ISO 27001 - Control - A12.1.4 Separation of development, testing and operational environments
ISO 27001 - Control - A12.2 Protection from malware
ISO 27001 - Control - A12.2.1 Controls against malware
ISO 27001 - Control - A12.3 Backup
ISO 27001 - Control - A12.3.1 Information backup
ISO 27001 - Control - A12.4 Logging and monitoring
ISO 27001 - Control - A12.4.1 Event logging
ISO 27001 - Control - A12.4.2 Protection of log information
ISO 27001 - Control - A12.4.3 Administrator and operator logs
ISO 27001 - Control - A12.4.4 Clock synchronisation
ISO 27001 - Control - A12.5 Control of operational software
ISO 27001 - Control - A12.5.1 Installation of software on operational systems
ISO 27001 - Control - A12.6 Technical vulnerability management
ISO 27001 - Control - A12.6.1 Management of technical vulnerabilities
ISO 27001 - Control - A12.6.2 Restrictions on software installation
ISO 27001 - Control - A12.7 Information systems audit considerations
ISO 27001 - Control - A12.7.1 Information systems audit controls
ISO 27001 - Control - A13 Communications security
ISO 27001 - Control - A13.1 Network security management
ISO 27001 - Control - A13.1.1 Network controls
ISO 27001 - Control - A13.1.2 Security of network services
ISO 27001 - Control - A13.1.3 Segregation in networks
ISO 27001 - Control - A13.2 Information transfer
ISO 27001 - Control - A13.2.1 Information transfer policies and procedures
ISO 27001 - Control - A13.2.2 Agreements on information transfer
ISO 27001 - Control - A13.2.3 Electronic messaging
ISO 27001 - Control - A13.2.4 Confidentiality or nondisclosure agreements
ISO 27001 - Control - A14 System acquisition, development & maintenance
ISO 27001 - Control - A14.1 Security requirements of information systems
ISO 27001 - Control - A14.1.1 Information security requirements analysis and specification
ISO 27001 - Control - A14.1.2 Securing application services on public networks
ISO 27001 - Control - A14.1.3 Protecting application services transactions
ISO 27001 - Control - A14.2 Security in development and support processes
ISO 27001 - Control - A14.2.1 Secure development policy
ISO 27001 - Control - A14.2.2 System change control procedures
ISO 27001 - Control - A14.2.3 Technical review of applications after operating platform changes
ISO 27001 - Control - A14.2.4 Restrictions on changes to software packages
ISO 27001 - Control - A14.2.5 Secure system engineering principles
ISO 27001 - Control - A14.2.6 Secure Development Environment
ISO 27001 - Control - A14.2.7 Outsourced development
ISO 27001 - Control - A14.2.8 System security testing
ISO 27001 - Control - A14.2.9 System acceptance testing
ISO 27001 - Control - A14.3 Test data
ISO 27001 - Control - A14.3.1 Protection of test data
ISO 27001 - Control - A15 Supplier relationships
ISO 27001 - Control - A15.1 Information security in supplier relationships
ISO 27001 - Control - A15.1.1 Information security policy for supplier relationships
ISO 27001 - Control - A15.1.2 Addressing security within supplier agreements
ISO 27001 - Control - A15.1.3 ICT supply chain
ISO 27001 - Control - A15.2 Supplier service delivery management
ISO 27001 - Control - A15.2.1 Monitoring and review of supplier services
ISO 27001 - Control - A15.2.2 Managing changes to supplier services
ISO 27001 - Control - A16 Information security incident management
ISO 27001 - Control - A16.1 Management of information security incidents & improvements
ISO 27001 - Control - A16.1.1 Responsibilities and procedures
ISO 27001 - Control - A16.1.2 Reporting information security events
ISO 27001 - Control - A16.1.3 Reporting information security weaknesses
ISO 27001 - Control - A16.1.4 Assessment of and decision on information security events
ISO 27001 - Control - A16.1.5 Response to information security incidents
ISO 27001 - Control - A16.1.6 Learning from information security incidents
ISO 27001 - Control - A16.1.7 Collection of evidence
ISO 27001 - Control - A17 Information security aspects of BCM
ISO 27001 - Control - A17.1 Information security continuity
ISO 27001 - Control - A17.1.1 Planning information security continuity
ISO 27001 - Control - A17.1.2 Implementing information security continuity
ISO 27001 - Control - A17.1.3 Verify, review and evaluate information security continuity
ISO 27001 - Control - A17.2 Redundancies
ISO 27001 - Control - A17.2.1 Availability of information processing facilities
ISO 27001 - Control - A18 Compliance
ISO 27001 - Control - A18.1 Compliance with legal and contractual requirements
ISO 27001 - Control - A18.1.1 Identification of applicable legislation and contractual requirements
ISO 27001 - Control - A18.1.2 Intellectual property rights
ISO 27001 - Control - A18.1.3 Protection of records
ISO 27001 - Control - A18.1.4 Privacy and protection of personally identifiable information
ISO 27001 - Control - A18.1.5 Regulation of cryptographic controls
ISO 27001 - Control - A18.2 Information security reviews
ISO 27001 - Control - A18.2.1 Independent review of information security
ISO 27001 - Control - A18.2.2 Compliance with security policies and standards
ISO 27001 - Control - A18.2.3 Technical compliance review
ISO 27001 - Control - All Controls

## Doc. Control
Document Control Page - This page to be updated in the event of changes/updates made to the core template
Risk Register
Risk Register Template Updates
Date | Version | Changes made by | Changes made
2017-04-20 | V1.0 | T. Bazdor | Site/Regional Risk Register initial draft
2017-05-16 | V1.2 | T. Bazdor | Various edits for clarification
2019-10-16 | V1.3 | T. Bazdor | Various edits to bring to current
2019-10-18 | V1.4 | T. Bazdor | Added risk catagories tab and assessment guide
2021-08-17 | V2.0 | T. Bazdor | Revised the risk register for use with ISO 27001 requirements
2022-03-10 | V2.1 | T. Bazdor | added Risk Process Guide
2023-11-10 | V3.0 | T. Bazdor | Signifigant update including modification of the register to better align with the MSI Common Risk Management Framework, updating "Key Terms" and the "Risk Assessment guide"
This template supports the "MSI Common Risk Management Framework", including any organization specific guidance, as found in the frameworks corresponding Appendices. This tempate may also be used with other risk programs.